Mifsud Financial Schedule

40 Rogers Drive, Kyneton VIC  |  Multi-Generational Build  |  Version 3 — March 2026

Construction loan @ 6.50%  |  Vendor finance @ RBA cash rate (currently 3.85%)  |  12-month build  |  Metricon progress payment schedule applied

| 1. PRE-CONSTRUCTION COSTS |  |  |
| --- | --- | --- |
| Cost Item | Estimate | Notes |
| Land Capability Assessment (ESO4 overlay) | $3,000 | Required before council will accept planning application |
| Planning Coordinator (council liaison) | $3,000 | As advised |
| Planning Permit Application Fee (Macedon Ranges Shire) | $1,580 | VIC 2025–26 fee: single dwelling ≤$1m = $1,580 |
| Planning Drawings | Included | Included in Metricon base price |
| Geotechnical / Soil Report | $1,500 | As quoted by Metricon (their contracted supplier) |
| Title Boundary Survey | $2,200 | Establish exact building envelope before plans drawn |
| Legal: Tenants-in-Common Deed + Title Review | $5,000 | Co-ownership deed, vendor finance deed, life tenancy + Tony's independent solicitor |
| PRE-CONSTRUCTION SUBTOTAL | $16,280 | Funded on current mortgage or from cash before construction loan |

ℹ Planning permit processing time at Macedon Ranges Shire is typically 2–4 months. Budget this timeline before construction loan approval. Planning drawings are included in the Metricon base price.

| 2. LAND ACQUISITION |  |  |
| --- | --- | --- |
| Item | Amount | Notes |
| Purchase price — upfront at settlement | $100,000 | Funded by MIL contribution (nets to $0 drawn from construction loan) |
| Vendor finance — balance | $150,000 | $50,000/yr × 3 years at RBA cash rate (currently 3.85%), reducing balance, separate from loan |
| Stamp duty — base case (assessed on $250k purchase price) | $10,070 | Conservative scenario — solicitor must confirm with SRO |
| Stamp duty — risk scenario (assessed on 62.5% × $1m title value) | $32,870 | Risk scenario — $22,800 gap. Resolve with solicitor before Stage 3 go/no-go |
| Conveyancing (land purchase) + SRO valuation | $2,600 |  |
| Vendor finance interest (3 years at 3.85% reducing balance) | $11,600 | Paid from cash flow, not from construction loan |

ℹ The $150k vendor finance balance (3×$50k to Tony) is NOT included in the loan figure — it is a separate ongoing payment obligation funded from cash flow after construction, at RBA cash rate interest.

| 3. KEY ASSUMPTIONS & WHAT TO VERIFY NEXT |  |  |
| --- | --- | --- |
| Item | Assumption Used | Action |
| NAB construction loan rate | 6.50% (staff ~7.77% + buffer) | Confirm with NAB lender before contract |
| RBA cash rate (vendor finance) | 3.85% (current) — variable | Document should specify rate review date (e.g. 1 July each year) |
| Stamp duty | $10,070 conservative / $32,870 risk scenario | PRIORITY: Resolve with solicitor before Stage 3 — $22,800 gap between scenarios |
| Planning permit timeframe | 2–4 months pre-build | Lodge pre-application enquiry with Macedon Ranges Shire |
| Developer contributions | $2,500 (allowance) | Confirm with Macedon Ranges Shire — may be nil for rural |
| Energy rating (NatHERS) | $1,200 — mandatory | Engage accredited NatHERS assessor with permit drawings |
| Building permit type | Private building surveyor | Confirm with Metricon — many volume builders engage own PBS |
| No LMI | Confirmed NAB staff benefit | Confirm with NAB HR/benefits team in writing |
| Loan establishment fee | $0 — NAB staff benefit | Confirm in writing. Progress inspection fees may still apply — verify with NAB |
| Agent commission | 1.6% (~$17k on $1.05m) | Obtain 2–3 appraisals from local agents |
| Contingency buffer | $30,000 — untouchable | Do not allocate until practical completion |

| 4. BUILD CONTRACT + EXTERNALS (Metricon) |  |  |
| --- | --- | --- |
| Category | Estimate | Notes |
| BASE BUILD & BUILDER UPGRADES |  |  |
| Base Build — Denver 47 (Metricon quote) | $467,000 | As quoted |
| Footprint and Garage Extension (~5 sq / ~45m²) | $102,000 | As advised |
| French Provincial Interior Package Upgrade | $50,000 | Includes ceiling height, facade, flooring, stone finishes |
| Grand Outdoor Upgrade | $50,000 | Builder package |
| SITE & COMPLIANCE |  |  |
| Septic System (rural, incl. treatment plant) | $30,000 | Rural installation |
| BAL 12.5 Bushfire Compliance | $12,500 | Zone requirement |
| Site Costs (adjusted for machinery savings) | $30,000 | $50k less $20k family machinery |
| FINISHES & FIXTURES |  |  |
| Electrical Upgrades (GPOs, lighting, data) | $12,000 | Feature lighting + extra circuits |
| Heating / Cooling Upgrade | $10,000 | Larger system for ~480m² |
| Window Furnishings (whole home) | $20,000 | Full house allowance |
| EXTERNAL & SERVICES |  |  |
| Concrete Pool (mid-range, installed) | $90,000 | Fully installed |
| Water Tanks — 45,000L total (dual 22.5kL) | $32,000 | Tanks + slab + plumbing |
| Whole House Filtration + UV System | $8,000 | Potable water quality |
| Driveway — Large Rural (adjusted) | $45,000 | $50k less $5k machinery saving |
| Landscaping (adjusted) | $30,000 | $35k less $5k bulk works saving |
| Fencing / Gates (acreage boundary + entry) | $15,000 | Perimeter + entry |
| BUILD + EXTERNAL + POOL SUBTOTAL | $994,000 |  |

| 5. BUILDING PERMIT & STATUTORY COSTS |  |  |
| --- | --- | --- |
| Cost Item | Estimate | Notes |
| VBA Building Permit Levy ($994k × 0.128%) | $1,272 | State government statutory levy — cannot be avoided |
| Private Building Surveyor (PBS) Fee | $4,500 | Includes inspections + occupancy permit; Metricon recommends PBS for speed |
| NatHERS Energy Rating Assessment (7-star mandatory) | $1,200 | Required for building permit application |
| Development Contributions (Macedon Ranges DCP — allowance) | $2,500 | Rural lots often lower — verify with Macedon Ranges Shire before submission |
| BUILDING PERMIT + STATUTORY SUBTOTAL | $9,472 |  |

| 6. HOLDING COSTS — CONSTRUCTION LOAN INTEREST (12 months @ 6.50%) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stage | % of Contract | Payment Due | Cumulative Drawn | Months to Next | Interest @ 6.50% |
| Deposit | 5.0% | $49,700 | $49,700 | 2 | $537 |
| Base | 20.0% | $198,800 | $248,500 | 2 | $2,692 |
| Frame | 20.0% | $198,800 | $447,300 | 2 | $4,846 |
| Lock Up | 25.0% | $248,500 | $695,800 | 3 | $11,307 |
| Fixing | 20.0% | $198,800 | $894,600 | 3 | $14,537 |
| Completion | 10.0% | $99,400 | $994,000 | 0 | $0 |
| TOTAL CONSTRUCTION INTEREST | 100% | $994,000 |  | 12 mo. | $33,919 |

ℹ Interest is charged only on drawn amounts after each Metricon milestone. The MIL $100k contribution offsets the $100k land upfront payment, so no net land interest is modelled.

| 7. COMPLETE PROJECT EXPOSURE — FULL COST ROLLUP |  |  |
| --- | --- | --- |
| Line Item | Amount | Running Total |
| Build Contract (Metricon — all inclusions + externals + pool) | $994,000 | $994,000 |
| Pre-Construction Costs (planning, surveys, legal — drawings included in build) | $16,280 | $1,010,280 |
| Building Permit + Statutory Costs | $9,472 | $1,019,752 |
| Land — Upfront $100k (funded by MIL; nets to $0 drawn from loan) | $100,000 | $1,119,752 |
| Land — Vendor Finance Balance ($150k deferred — NOT in loan) | $150,000 | $1,269,752 |
| Stamp Duty — Conservative / base case (see Section 2 for risk scenario) | $10,070 | $1,279,822 |
| Conveyancing (land purchase) + Valuation (SRO) | $2,600 | $1,282,422 |
| Loan Establishment (NAB staff — $0) + Progress Inspections (confirm with NAB) | $0 | $1,282,422 |
| Construction Loan Interest (12 months — progressive drawdowns) | $33,919 | $1,316,341 |
| Pre-Sale Renovation (current home) | $20,000 | $1,336,341 |
| Real Estate Agent Commission + Conveyancing (sale) | $18,500 | $1,354,841 |
| Contingency Buffer (untouchable) | $30,000 | $1,384,841 |
| GROSS TOTAL PROJECT EXPOSURE |  | $1,384,841 |
| Less: MIL Contribution ($100k) | −$100,000 | $1,284,841 |
| Less: Equity from Sale of Current Home (midpoint estimate) | −$385,000 | $899,841 |
| ESTIMATED NEW LOAN REQUIRED (BASE CASE) |  | $899,841 |

ℹ The $150k vendor finance balance (3×$50k to Tony) is NOT included in the loan figure — it is a separate ongoing payment obligation funded from cash flow after construction, at RBA cash rate interest.

This schedule is a planning tool only and does not constitute financial, legal, or taxation advice. All figures should be verified with your NAB lender, solicitor, and the Victorian State Revenue Office before any commitment is made.

Prepared for Ryan Mifsud  |  40 Rogers Drive, Kyneton  |  March 2026  |  Pre-meeting working document — not for distribution